## Install & Pull Data
CUSTOMER | WELL # | INSTALL | MOTOR | FLOW | BHT | PUMP | CABLE LENGTH | RUNTIME (Excel Calculated) | Status | PULL DATE | COMMENTS | Reason for Pull | SEAL | New Screen | warranty | credit back | W/L | R/NR/Waiting | Failure Points | quote /price
CENOVUS | B05P05-1 | 2020-12-20 | 84HP | 450m3 | 220°C | SJ2800 38 STAGE | 615m | 400 | failed | 2022-01-24 | The cause for the downhole short is likely attributed to a well fluid contamination burn in the motor stator. The well fluid contamination throughout the system resulted from a seal failure likely due to low/no flow events throughout the operation | Well Fluid Contamination | Version 1 | no | no | yes | w | NR | Motor Stator
CENOVUS | E08P02 | 2021-02-11 | 84HP | 360m3 | 220°C | SJ2800 38 STAGE | 810m | 888 |  |  |  |  | Version 1 | no |  |  | w | R
CONOCO | 262-1 P02 | 2021-03-29 | 84HP | 840m3 | 215°C | SJ5500 41 STAGE | 519m | 275 | Failed Elect | 2021-12-29 | The cause for the downhole short is likely attributed to the presence of conductive/low dielectric fluid and insulation degradation resulting in the burn in the motor stator and ultimately failed the system. The well fluid appears to have traversed the seal section. | Downhole Short | Version 1 | no | no | yes | w | NR | Motor Stator
CENOVUS | L03P06 | 2021-04-16 | 108HP | 850m3 | 215°C | SJ5500 29 STAGE | 589m | 85 | Failed Elect | 2021-07-10 | The cause for the electrical failure in the motor that the system was pulled for was due to well fluid contamination into the motor. The reason for well fluid contamination was due to exceeding volumetric capacity of the motor oil contained in the seal, motor and below motor bellows under vacuum during thermal contraction, which exceeded the differential pressure limitations of upper guide mechanical shaft seal and duel nested bellows | Well Fluid Contamination | Version 1 | no | yes | no | w | NR | Motor Stator
CENOVUS | L03P07 | 2021-04-29 | 84HP | 650m3 | 220°C | SJ4200 36 STAGE | 629m | 254 | Failed Elect | 2022-01-08 | The cause for the downhole short can be attributed to a well fluid contamination burn in the Pothead. The well fluid contamination throughout the system resulted from a seal pressurization failure due to low/no flow events during an abnormal amount of no production events throughout the operation. | Well Fluid Contamination | Version 1 | no | no | yes | w | NR | Pothead
SUNCOR | 6P10 | 2021-06-19 | 60HP | 700m3 | 210°C | SJ4200 18 STAGE | 616m | 168 | cable damage | 2021-12-04 | The cause for the electrical failure found in the motor was a direct result of overheating, and the overheating is most likely due to the ESP operating for an extended period under extreme load fluctuation conditions (for the last four days of operation). It is unknown if this type of operation was intended (manual) or if there was a surface equipment issue with the drive/controller. | Overheating | Version 1 | no | stop pay | no | w | NR | Motor Stator
SUNCOR | 2N8 | 2021-09-30 | 60HP | 350m3 | 198°C | SJ2800 22 STAGE | 455m | 432 | possible broken shaft | 2022-12-06 |  | Idle Amps | Version 1 | no |  |  | w | NR | Seal
CONOCO | 262-2 P11 | 2021-10-12 | 132HP | 1250m3 | 215°C | SJ8000 35 STAGE | 655m | 140 | failed shaft | 2022-03-01 | The cause of the No production/Idle Amps was a broken shaft in the seal; The broken shaft was due to excessive mechanical heat transfer from a seized radial support bearing in the seal head due to loss of lubricity impacted by sand accumulation in the upper lab section. | No Production | Version 1 | no | no | no | w | NR | Seal
CONOCO | 265-2 P07 | 2021-11-17 | 108HP | 1100m3 | 210°C | SJ8000 29 STAGE/GINPSH | 600m | 144 | Failed Elect | 2022-04-10 | The cause of the downhole short is attributed to the presence of conductive fluid (water and bitumen) and insulation degradation in the motor; the short was located just below the motor female pins. | Downhole Short | Version 1 | no | no | no | w | NR | Motor Stator
CENOVUS | W19P02 | 2021-11-28 | 108HP | 480m3 | 236°C | SJ4200 36 STAGE | 1016m | 21 | Failed Elect | 2021-12-19 | The cause for the down hole short for which this unit was pulled can be attributed to a contamination burn in the head end of the motor that was a result of a seal pressurization failure and probable insulation degradation to motor components from low/no flow events during an abnormal amount of no production ride through operation. | No Production | Version 2 | no | no | yes | w | NR | Motor Stator
CENOVUS | L09P06 | 2021-11-30 | 132HP | 750m3 | 215°C | SJ5500 41 STAGE | 629m | 83 | Failed Elect | 2022-02-21 | The cause for the downhole short is likely attributed to a well fluid contamination burn in the motor stator. The well fluid contamination throughout the system resulted from the seal failure likely due to low/no flow events throughout the operation combined with reduced seal volumetric flow equalization rates. | Well Fluid Contamination | Version 2 | no | no | yes | w | NR | Motor Stator
STRATHCONA | D02-P02 | 2021-12-14 | 60HP | 350m3 | 215°C | SJ2800 38 STAGE | 600m | 273 | Failed Elect | 2022-09-13 |  | Downhole Short | Version 1 | no | no |  | w | NR | Motor Stator
STRATHCONA | 109-P1 | 2021-12-20 | 84HP | 400m3 | 210°C | SJ4200 24 stg/GIN | 810m | 108 | PCP pump | 2022-04-07 | system is stabilized, start up issues change pcp | No Production | Version 1 | no | no | no | w | NR | Seal
CONOCO | 262-2 P05 | 2022-01-16 | 108HP | 1000m3 | 230°C | SJ6500 38 STAGE | 500m | 549 |  |  |  |  | Version 1 | no |  |  | w | R
CONOCO | 264-3 P08 | 2022-01-18 | 108HP | 950m3 | 215°C | SJ8000 35 STAGE | 549m | 354 | Failed Elect | 2023-01-07 | electrically failed | Unknown | Version 2 | no |  |  | w | NR | Unknown
CNOOC | 09P05 | 2022-03-15 | 60HP | 312m3 | 170°C | SJ2800 15 Stage/GINPSH | 370m | 229 | not failed | 2022-10-30 | pulled and rebuilding to run in another | Rebuild | Version 2.5 | no |  |  | w | NR | Unknown
CNOOC | 05P01 | 2022-03-16 | 60HP | 480m3 | 185°C | SJ4200 12 stage/SGNPSH | 375m | 54 | seal fail | 2022-05-09 | failed broken shaft, no prod both ways | No Production | Version 2.5 | no | yes |  | w | NR | Broken Shaft
STRATHCONA | D02-P04 | 2022-03-23 | 60HP | 250m3 | 210°C | SJ2800 38 STAGE | 745m | 483 |  |  |  |  | Version 2.5 | no |  |  | w | R
STRATHCONA | D04-P09 | 2022-04-03 | 60HP | 450m3 | 220°C | SJ2800 38 STAGE | 950m | 169 | Failed Elect | 2022-09-19 | bucket system going back in baker | Downhole Short | Version 2.5 | no | no |  | w | NR | Seal
STRATHCONA | D02P08 | 2022-05-09 | 60Hp | 200m3 | 210°C | SJ2800 38 STAGE | 915m | 179 |  | 2022-11-04 | using backup 2 | Downhole Short | Version 2.5 | no |  |  | w | NR | Seal/Motor
STRATHCONA | D02P07 | 2022-05-14 | 60Hp | 220m3 | 210°C | SJ2800 45 STAGE | 858m | 60 | seal fail | 2022-07-13 | Tear down Completed; Seal shaft was not broken, the system held pressure test, Stator was found shorted, found burn at the upper-end coil of Stator also, found water in the seal, motor and BMB, no bitumen in the system, most probably steam entered the system as a result of stator short /explosion. When the unit was retrieved, steam was converted into water. Burn in Stator can be either due to handling during assembly or heat from the operation, waiting on operation data. | Steam Contamination | Version 2.5 | no | yes |  | w | NR | Motor Stator
CENOVUS | G09P02 | 2022-06-20 | 168Hp | 1000m3 | 220°C | SJ8000 47 STAGE | 830m | 66 | failed elect | 2022-08-25 | Tear down Completed; Seal shaft was not broken, the system held pressure test, Stator was found short. Seal, motor and BMB had well fluid (bitumen and water). The Stator was not dissected to locate the fault, but the short is a result of well fluid contamination due to cycling, as shown in the production data. | Downhole Short | Version 3.0 | no |  |  | w | NR | Seal
CENOVUS | L02P06 | 2022-06-29 | 168Hp | 1000m3 | 220°C | SJ8000 47 STAGE | 570m | 144 | failed | 2022-11-20 | lower meg readings at landing | Downhole Short | Version 3.0 | no |  |  | w | NR | Seal
CENOVUS | B07P17 | 2022-07-11 | 84Hp | 450m3 | 210°C | SJ4200 42 STAGE | 650m | 106 | failed | 2022-10-25 | utilizing ver 2.5 for trial purpose to get run time | Downhole Short | Version 2.5 | no |  |  | w | NR | Seal
CENOVUS | B13P05 | 2022-07-23 | 60hp | 400m3 | 210°C | SJ2800 38 STAGE | 575m | 361 |  |  |  |  | Version 3.0 | no |  |  | w | R
CENOVUS | E26P10 | 2022-07-30 | 132Hp | 950m3 | 220°C | SJ8000 47 STAGE | 930m | 354 |  |  | aviation bomb found on location standby |  | Version 3.0 | no |  |  | w | R
CENOVUS | W29P01 | 2022-07-31 | 132Hp | 1000m3 | 240°C | SJ8000 47 STAGE | 958m | 37 | Failed Elect | 2022-09-06 |  | Downhole Short | Version 3.0 | no |  |  | w | NR | Seal
CENOVUS | J03P08 | 2022-08-08 | 84Hp | 600m3 | 210°C | SJ4200 36 STAGE | 605m | 345 |  |  |  |  | Version 3.0 | no |  |  | w | R
STRATHCONA | D02P07 | 2022-08-20 | 60Hp | 250m3 | 210°C | SJ2800 38 STAGE | 858m | 170 | failure | 2023-02-06 | using backup 3 | Downhole Short | Version 2.5 | no |  |  | w | NR | Motor Stator
CONOCO | 263-1 P04 | 2022-08-28 | 60hp | 775m3 | 210°C | SJ6500 23 STAGE | 540m | 325 |  |  |  |  | Version 3.0 | no |  |  | w | R
SUNCOR | 5P8 | 2022-09-17 | 60Hp | 600m3 | 198°C | SJ4200 18 STAGE | 480m | 305 |  |  |  |  | Version 2.5 | no |  |  | w | R
CENOVUS | B07P14 | 2022-10-07 | 108Hp | 500m3 | 225°C | SJ5500 41 STAGE | 580 | 285 |  |  |  |  | Version 3.0 | no |  |  | w | R |  | 173000
STRATHCONA | D02P08 | 2022-11-04 | 60Hp | 700m3 | 210°C | SJ2800 38 STAGE/SGNPSH | 915m | 101 | electrical failure | 2023-02-13 | backup #4 used for this system | Downhole Short | Version 2.5 | new screen |  |  | w | NR | Seal | 216366
CENOVUS | W19P10-1 | 2022-11-06 | 168Hp | 800m3 | 235°C | SJ8000 53 STAGE | 820 | 190 | electrical failure | 2023-05-15 |  | Unknown | Version 3.0- New screen | new screen |  |  | w | NR | Unknown | 188240
CONOCO | 262-2P02 | 2022-11-19 | 84HP | 840m3 | 205°C | SJ6500 33 STAGE | 650m | 242 |  |  |  |  | Version 3.0- New screen | new screen |  |  | w | R |  | 236068.46
CONOCO | 261-3 P11 | 2022-12-03 | 60HP | 740m3 | 205°C | SJ5500 29 STAGE | 620m | 228 |  |  | backup #4 for strathcona for shelf |  | Version 3.0- New screen | new screen |  |  | w | R |  | 191000
CNRL | E3P | 2022-12-29 | 108HP | 700m3 | 227°C | SJ5500 47 STAGE | 776m | 41 | electrical failure | 2023-02-08 | motor winding/seal flood | Unknown | Version 3.0- New screen | new screen |  |  | w | NR | Unknown | 189314.63
STRATHCONA | 206p06 | 2023-01-11 | 60HP | 350m3 | 215 | SJ2800 22 stage/sgnpsh | 660m | 131 | electrical failure | 2023-05-22 | lots of steam and flashing on this well | Unknown | Version 2.5 | new screen |  |  | w | NR | Unknown | 192120.68
STRATHCONA | D03P06 | 2023-01-28 | 60HP | 250m3 | 210°C | SJ2800 45 STAGE/SGNPSH | 809m | 57 | failed | 2023-03-26 |  | Unknown | Version 2.5 | new screen |  |  | w | NR | Unknown | 57000
STRATHCONA | 204P10 | 2023-02-17 | 84HP | 430m3 | 215°C | SJ4200 24 stage | 890m | 85 | failed | 2023-05-13 | run in hole, shorted 2 times, 3rd charm damaged hanger | Unknown | Version 3.0- New screen |  |  |  | w | NR | Unknown | 358478.3
HARVEST | 102-P02 | 2023-04-03 | 60HP | 350m3 | 235°C | SJ2800 38 stage D-15 | 570m | 107 |  |  |  |  | Version 3.5 |  |  |  | w | R |  | 185157.68
Suncor | 3P2 | 2023-05-18 | 60HP | 450m3 | 200°C | SJ2800 22 Stage | 410m | 62 |  |  |  |  | Version 3.5 |  |  |  | w | R |  | 155000
STRATHCONA | 206P07 | 2023-07-13 | 84HP | 450m3 | 205°C | SJ2800 30/H2X/Slugger | 608m | 6 | Running |  | SLUGGER |  | Version 3.5 |  |  |  | w | R
STRATHCONA | 206P06 | 2023-05-27 | 84HP | 450m4 | 205°C | SJ2800 30/H2X/Slugger | 746m | 53 | Running |  | SLUGGER-latest seal section,used motor/cable |  | Version 3.5 |  |  |  | w | R |  | 135942.88
Formulas:
RUNTIME (Excel Calculated) = IF([R/NR/Waiting]="Waiting","",IF([R/NR/Waiting]="R",TODAY()-[INSTALL],IF([R/NR/Waiting]="NR",[PULL DATE]-[INSTALL],IF(ISBLANK([R/NR/Waiting]),""))))

## Sheet2
FIELD | CUSTOMER | WELL # | INSTALL | MOTOR | FLOW | BHT | PUMP | CABLE LENGTH | RUNTIME | RUN/NO RUN | PULL DATE | COMMENTS | SEAL | intake | DIFA | warranty | W/L | R/NR | quote /price
Christina lake | CENOVUS | B05P05-1 | 2020-12-20 | 84HP | 450m3 | 220°C | SJ2800 38 STAGE | 615 | 400 | failed | 2022-01-24 | electrical failure due to seal failure | ver 1 |  |  | no | w | NR
Foster Creek | CENOVUS | E08P02 | 2021-02-11 | 84HP | 360m3 | 220°C | SJ2800 38 STAGE | 810 | 858 |  |  |  | ver 1 |  |  |  | w | R
Surmont | CONOCO | 262-1 P02 | 2021-03-29 | 84HP | 840m3 | 215°C | SJ5500 41 STAGE | 519m | 275 | Failed Elect | 2021-12-29 | root/C- seal trial payback | ver 1 |  | feb 17th | no | w | NR
Christina lake | CENOVUS | L03P06 | 2021-04-16 | 108HP | 850m3 | 215°C | SJ5500 29 STAGE | 589 | 85 | Failed Elect | 2021-07-10 | root cause seal | ver 1 |  | completed | yes | w | NR
Christina lake | CENOVUS | L03P07 | 2021-04-29 | 84HP | 650m3 | 220°C | SJ4200 36 STAGE | 629 | 254 | Failed Elect | 2022-01-08 | electrical failure root cause was seal | ver 1 |  | jan 27th | no | w | NR
FireBag | SUNCOR | 6P10 | 2021-06-19 | 60HP | 700m3 | 210°C | SJ4200 18 STAGE | 616m | 168 | cable damage | 2021-12-04 | ran no production for several hours no flow | ver 1 |  |  | stop pay | w | NR
FireBag | SUNCOR | 2N8 | 2021-09-30 | 60HP | 350m3 | 198°C | SJ2800 22 STAGE | 455m | 432 | possible broken shaft | 2022-12-06 |  | ver 1 |  | Jan 16 done |  | w | NR
Surmont | CONOCO | 262-2 P11 | 2021-10-12 | 132HP | 1250m3 | 215°C | SJ8000 35 STAGE | 655m | 140 | failed shaft | 2022-03-01 | sand issues | ver 1 |  | april 7th | no | w | NR
Surmont | CONOCO | 265-2 P07 | 2021-11-17 | 108HP | 1100m3 | 210°C | SJ8000 29 STAGE/GINPSH | 600m | 144 | Failed Elect | 2022-04-10 | plant upset 30hz 1.5hr/shorted | ver 1 |  | may 19th | no | w | NR
Foster Creek | CENOVUS | W19P02 | 2021-11-28 | 108HP | 480m3 | 236°C | SJ4200 36 STAGE | 1016 | 21 | Failed Elect | 2021-12-19 | used warranty unit for L03P06 electrical failure | ver 2 |  | jan 19th | no | w | NR
Christina lake | CENOVUS | L09P06 | 2021-11-30 | 132HP | 750m3 | 215°C | SJ5500 41 STAGE | 629 | 83 | Failed Elect | 2022-02-21 | rerated to 108hp , lifted one joint, unstable | ver 2 |  |  | no | w | NR
Lindbergh | STRATHCONA | D02-P02 | 2021-12-14 | 60HP | 350m3 | 215°C | SJ2800 38 STAGE | 600m | 273 | Failed Elect | 2022-09-13 | schlum replacing | ver 1 |  | Nov 18 done | no | w | NR
Orion | STRATHCONA | 109-P1 | 2021-12-20 | 84HP | 400m3 | 210°C | SJ4200 24 stg/GIN | 810m | 108 | PCP pump | 2022-04-07 | system is stabilized, start up issues change pcp | ver 1 |  | sent to DK | no | w | NR
Surmont | CONOCO | 262-2 P05 | 2022-01-16 | 108HP | 1000m3 | 230°C | SJ6500 38 STAGE | 500m | 519 |  |  |  | ver 1 |  |  |  | w | R
Surmont | CONOCO | 264-3 P08 | 2022-01-18 | 108HP | 950m3 | 215°C | SJ8000 35 STAGE | 549m | 354 | Failed Elect | 2023-01-07 | electrically failed | ver 2 |  | send march | ? | w | NR
Long Lake | CNOOC | 09P05 | 2022-03-15 | 60HP | 312m3 | 170°C | SJ2800 15 Stage/GINPSH | 370m | 229 | not failed | 2022-10-30 | pulled and rebuilding to run in another | ver 2.5 |  | JAN | no | w | NR
Long Lake | CNOOC | 05P01 | 2022-03-16 | 60HP | 480m3 | 185°C | SJ4200 12 stage/SGNPSH | 375m | 54 | seal fail | 2022-05-09 | failed broken shaft, no prod both ways | ver2.5 |  | june 9 th 2022 | yes | w | NR
Lindbergh | STRATHCONA | D02-P04 | 2022-03-23 | 60HP | 250m3 | 210°C | SJ2800 38 STAGE | 745m | 453 |  |  |  | ver 2.5 |  |  |  | w | R
Lindbergh | STRATHCONA | D04-P09 | 2022-04-03 | 60HP | 450m3 | 220°C | SJ2800 38 STAGE | 950m | 169 | Failed Elect | 2022-09-19 | bucket system going back in baker | ver 2.5 |  | Nov 16 done | no | w | NR
Lindbergh | STRATHCONA | D02P08 | 2022-05-09 | 60Hp | 200m3 | 210°C | SJ2800 38 STAGE | 915m | 175 | failure | 2022-10-31 | failed during turnaround | ver2.5 |  | DEC 1 done | no | w | NR
Lindbergh | STRATHCONA | D02P07 | 2022-05-14 | 60Hp | 220m3 | 210°C | SJ2800 45 STAGE | 858m | 60 | seal fail | 2022-07-13 | motor winding failure at head | ver2.5 |  | august | yes | w | NR
Christina lake | CENOVUS | G09P02 | 2022-06-20 | 168Hp | 1000m3 | 220°C | SJ8000 47 STAGE | 830 | 66 | failed elect | 2022-08-25 | electrical failure TBD-well failed TBD | ver 3.0 |  | 2023-09-12 | no | w | NR
Christina lake | CENOVUS | L02P06 | 2022-06-29 | 168Hp | 1000m3 | 220°C | SJ8000 47 STAGE | 570 | 144 |  | 2022-11-20 | lower meg readings at landing | ver 3.0 |  | 2023-01-16 | no | w | NR
Christina lake | CENOVUS | B07P17 | 2022-07-11 | 84Hp | 450m3 | 210°C | SJ4200 42 STAGE | 650 | 106 |  | 2022-10-25 | utilizing ver 2.5 for trial purpose to get run time | ver 2.5 |  | JAN send | no | w | NR
Christina lake | CENOVUS | B13P05 | 2022-07-23 | 60hp | 400m3 | 210°C | SJ2800 38 STAGE | 575 | 331 |  |  |  | ver 3.0 |  |  |  | w | R
Foster Creek | CENOVUS | E26P10 | 2022-07-30 | 132Hp | 950m3 | 220°C | SJ8000 47 STAGE | 930 | 324 |  |  |  | ver 3.0 |  |  |  | w | R
Foster Creek | CENOVUS | W29P01 | 2022-07-31 | 132Hp | 1000m3 | 240°C | SJ8000 47 STAGE | 958 | 37 | Failed Elect | 2022-09-06 | electrical issue unbalanced-well failure | ver 3.0 |  | 2023-09-19 | no | w | NR | 203207.38
Christina lake | CENOVUS | J03P08 | 2022-08-08 | 84Hp | 600m3 | 210°C | SJ4200 36 STAGE | 605 | 315 |  |  |  | ver 3.0 |  |  |  | w | R | 178697.32
Lindbergh | STRATHCONA | D02P07 | 2022-08-20 | 60Hp | 250m3 | 210°C | SJ2800 38 STAGE | 858m | 170 | failure | 2023-02-06 | using backup 3 | ver2.5 |  | done may | ? | w | NR
Surmont | CONOCO | 263-1 P04 | 2022-08-28 | 60hp | 775m3 | 210°C | SJ6500 23 STAGE | 540m | 295 |  |  |  | ver 3.0 |  |  |  | w | R
FireBag | SUNCOR | 5P8 | 2022-09-23 | 60Hp | 600m3 | 198°C | SJ4200 18 STAGE | 480m | 269 |  |  |  | ver 2.5 |  |  |  | w | R
Christina lake | CENOVUS | B07P14 | 2022-10-07 | 108Hp | 500m3 | 225°C | SJ5500 41 STAGE | 580 | 255 |  |  |  | ver 3.0 |  |  |  | w | R | 173000
Lindbergh | STRATHCONA | D02P08 | 2022-11-04 | 60Hp | 700m3 | 210°C | SJ2800 38 STAGE/SGNPSH | 915m | 101 | electrical failure | 2023-02-13 | backup #4 used for this system | Ver2.5 | new screen | done may | ? | w | NR | 216366
Foster Creek | CENOVUS | W19P10-1 | 2022-11-06 | 168Hp | 800m3 | 235°C | SJ8000 53 STAGE | 820 | 190 | electrical failure | 2023-05-15 |  | ver 3.0 | new screen | JUNE |  | w | NR | 188240
Surmont | CONOCO | 262-2P02 | 2022-11-19 | 84HP | 840m3 | 205°C | SJ6500 33 STAGE | 650m | 212 |  |  |  | ver 3.0 | new screen |  |  | w | R | 236068.46
Surmont | CONOCO | 261-3 P11 | 2022-12-03 | 60HP | 740m3 | 205°C | SJ5500 29 STAGE | 620m | 198 |  |  |  | ver 3.0 | new screen |  |  | w | R | 191000
Kirby South | CNRL | E3P | 2022-12-29 | 108HP | 700m3 | 227°C | SJ5500 47 STAGE | 776m | 41 | electrical failure | 2023-02-08 | motor winding/seal flood | ver 3.0 | new screen | done | ? | w | NR | 189314.63
Orion | STRATHCONA | 206p06 | 2023-01-11 | 60HP | 350m3 | 215°C | SJ2800 22 stage/sgnpsh | 660m | 131 | electrical failure | 2023-05-22 | lots of steam and flashing on this well | ver 2.5 | new screen | JUNE |  | w | NR | 192120.68
Lindbergh | STRATHCONA | D03P06 | 2023-01-28 | 60HP | 250m3 | 210°C | SJ2800 45 STAGE/SGNPSH | 809m | 57 | electrical failure | 2023-03-26 | used warranty unit | ver 2.5 | new screen | done may | ? | w | NR | 57000
Orion | STRATHCONA | 204P10 | 2023-02-17 | 84HP | 430m3 | 215°C | SJ4200 24 stage | 890m | 85 | bucket | 2023-05-13 | run in hole, shorted 2 times, 3rd charm damaged hanger | ver 3.0 | new screen | JUNE |  | w | NR | 358478.3
LEISMER | HARVEST | 102-P02 | 2023-04-03 | 60HP | 350m3 | 235°C | SJ2800 38 stage D-15 | 570m | 77 |  |  |  | ver 3.0 | new screen |  |  | w | R | 185157.68
Orion | STRATHCONA | 206P06 | 2023-05-27 | 84HP | 450m4 | 205°C | SJ2800 30/H2X/Slugger | 746m | 23 |  |  | SLUGGER-latest seal section,used motor/cable | ver 3.5 | new screen |  |  | w | R | 135942.88
Firebag | Suncor | 3P2 | 2023-06-01 | 60HP | 450m3 | 200°C | SJ2800 22 Stage | 410m | 18 |  |  |  | ver 3.5 | new screen |  |  | w | R | 155000
| CNOOC | [5 empty] | SJ4200 12 stage/SGNPSH |  |  | waiting |  | motor/seals went to suncor-pumps inventory | ver 3.0 | new screen |  |  | w | NR

## Sheet1
CUSTOMER | WELL # | INSTALL | MOTOR | FLOW | BHT | PUMP | CABLE LENGTH | RUNTIME (Excel Calculated) | Status | PULL DATE | COMMENTS | Reason for Pull | SEAL | New Screen | warranty | credit back | W/L | R/NR/Waiting | Failure Points | quote /price
CENOVUS | B05P05-1 | 2020-12-20 | 84HP | 450m3 | 220°C | SJ2800 38 STAGE | 615m | 400 | failed | 2022-01-24 | The cause for the downhole short is likely attributed to a well fluid contamination burn in the motor stator. The well fluid contamination throughout the system resulted from a seal failure likely due to low/no flow events throughout the operation | Well Fluid Contamination | Version 1 | no | no | yes | w | NR | Motor Stator
CENOVUS | E08P02 | 2021-02-11 | 84HP | 360m3 | 220°C | SJ2800 38 STAGE | 810m | 858 |  |  |  |  | Version 1 | no |  |  | w | R
CONOCO | 262-1 P02 | 2021-03-29 | 84HP | 840m3 | 215°C | SJ5500 41 STAGE | 519m | 275 | Failed Elect | 2021-12-29 | The cause for the downhole short is likely attributed to the presence of conductive/low dielectric fluid and insulation degradation resulting in the burn in the motor stator and ultimately failed the system. The well fluid appears to have traversed the seal section. | Downhole Short | Version 1 | no | no | yes | w | NR | Motor Stator
CENOVUS | L03P06 | 2021-04-16 | 108HP | 850m3 | 215°C | SJ5500 29 STAGE | 589m | 85 | Failed Elect | 2021-07-10 | The cause for the electrical failure in the motor that the system was pulled for was due to well fluid contamination into the motor. The reason for well fluid contamination was due to exceeding volumetric capacity of the motor oil contained in the seal, motor and below motor bellows under vacuum during thermal contraction, which exceeded the differential pressure limitations of upper guide mechanical shaft seal and duel nested bellows | Well Fluid Contamination | Version 1 | no | yes | no | w | NR | Motor Stator
CENOVUS | L03P07 | 2021-04-29 | 84HP | 650m3 | 220°C | SJ4200 36 STAGE | 629m | 254 | Failed Elect | 2022-01-08 | The cause for the downhole short can be attributed to a well fluid contamination burn in the Pothead. The well fluid contamination throughout the system resulted from a seal pressurization failure due to low/no flow events during an abnormal amount of no production events throughout the operation. | Well Fluid Contamination | Version 1 | no | no | yes | w | NR | Pothead
SUNCOR | 6P10 | 2021-06-19 | 60HP | 700m3 | 210°C | SJ4200 18 STAGE | 616m | 168 | cable damage | 2021-12-04 | The cause for the electrical failure found in the motor was a direct result of overheating, and the overheating is most likely due to the ESP operating for an extended period under extreme load fluctuation conditions (for the last four days of operation). It is unknown if this type of operation was intended (manual) or if there was a surface equipment issue with the drive/controller. | Overheating | Version 1 | no | stop pay | no | w | NR | Motor Stator
SUNCOR | 2N8 | 2021-09-30 | 60HP | 350m3 | 198°C | SJ2800 22 STAGE | 455m | 432 | possible broken shaft | 2022-12-06 |  | Idle Amps | Version 1 | no |  |  | w | NR | Seal
CONOCO | 262-2 P11 | 2021-10-12 | 132HP | 1250m3 | 215°C | SJ8000 35 STAGE | 655m | 140 | failed shaft | 2022-03-01 | The cause of the No production/Idle Amps was a broken shaft in the seal; The broken shaft was due to excessive mechanical heat transfer from a seized radial support bearing in the seal head due to loss of lubricity impacted by sand accumulation in the upper lab section. | No Production | Version 1 | no | no | no | w | NR | Seal
CONOCO | 265-2 P07 | 2021-11-17 | 108HP | 1100m3 | 210°C | SJ8000 29 STAGE/GINPSH | 600m | 144 | Failed Elect | 2022-04-10 | The cause of the downhole short is attributed to the presence of conductive fluid (water and bitumen) and insulation degradation in the motor; the short was located just below the motor female pins. | Downhole Short | Version 1 | no | no | no | w | NR | Motor Stator
CENOVUS | W19P02 | 2021-11-28 | 108HP | 480m3 | 236°C | SJ4200 36 STAGE | 1016m | 21 | Failed Elect | 2021-12-19 | The cause for the down hole short for which this unit was pulled can be attributed to a contamination burn in the head end of the motor that was a result of a seal pressurization failure and probable insulation degradation to motor components from low/no flow events during an abnormal amount of no production ride through operation. | No Production | Version 2 | no | no | yes | w | NR | Motor Stator
CENOVUS | L09P06 | 2021-11-30 | 132HP | 750m3 | 215°C | SJ5500 41 STAGE | 629m | 83 | Failed Elect | 2022-02-21 | The cause for the downhole short is likely attributed to a well fluid contamination burn in the motor stator. The well fluid contamination throughout the system resulted from the seal failure likely due to low/no flow events throughout the operation combined with reduced seal volumetric flow equalization rates. | Well Fluid Contamination | Version 2 | no | no | yes | w | NR | Motor Stator
STRATHCONA | D02-P02 | 2021-12-14 | 60HP | 350m3 | 215°C | SJ2800 38 STAGE | 600m | 273 | Failed Elect | 2022-09-13 |  | Downhole Short | Version 1 | no | no |  | w | NR | Motor Stator
STRATHCONA | 109-P1 | 2021-12-20 | 84HP | 400m3 | 210°C | SJ4200 24 stg/GIN | 810m | 108 | PCP pump | 2022-04-07 | system is stabilized, start up issues change pcp | No Production | Version 1 | no | no | no | w | NR | Seal
CONOCO | 262-2 P05 | 2022-01-16 | 108HP | 1000m3 | 230°C | SJ6500 38 STAGE | 500m | 519 |  |  |  |  | Version 1 | no |  |  | w | R
CONOCO | 264-3 P08 | 2022-01-18 | 108HP | 950m3 | 215°C | SJ8000 35 STAGE | 549m | 354 | Failed Elect | 2023-01-07 | electrically failed | Unknown | Version 2 | no |  |  | w | NR | Unknown
CNOOC | 09P05 | 2022-03-15 | 60HP | 312m3 | 170°C | SJ2800 15 Stage/GINPSH | 370m | 229 | not failed | 2022-10-30 | pulled and rebuilding to run in another | Rebuild | Version 2.5 | no |  |  | w | NR | Unknown
CNOOC | 05P01 | 2022-03-16 | 60HP | 480m3 | 185°C | SJ4200 12 stage/SGNPSH | 375m | 54 | seal fail | 2022-05-09 | failed broken shaft, no prod both ways | No Production | Version 2.5 | no | yes |  | w | NR | Broken Shaft
STRATHCONA | D02-P04 | 2022-03-23 | 60HP | 250m3 | 210°C | SJ2800 38 STAGE | 745m | 453 |  |  |  |  | Version 2.5 | no |  |  | w | R
STRATHCONA | D04-P09 | 2022-04-03 | 60HP | 450m3 | 220°C | SJ2800 38 STAGE | 950m | 169 | Failed Elect | 2022-09-19 | bucket system going back in baker | Downhole Short | Version 2.5 | no | no |  | w | NR | Seal
STRATHCONA | D02P08 | 2022-05-09 | 60Hp | 200m3 | 210°C | SJ2800 38 STAGE | 915m | 179 |  | 2022-11-04 | using backup 2 | Downhole Short | Version 2.5 | no |  |  | w | NR | Seal/Motor
STRATHCONA | D02P07 | 2022-05-14 | 60Hp | 220m3 | 210°C | SJ2800 45 STAGE | 858m | 60 | seal fail | 2022-07-13 | Tear down Completed; Seal shaft was not broken, the system held pressure test, Stator was found shorted, found burn at the upper-end coil of Stator also, found water in the seal, motor and BMB, no bitumen in the system, most probably steam entered the system as a result of stator short /explosion. When the unit was retrieved, steam was converted into water. Burn in Stator can be either due to handling during assembly or heat from the operation, waiting on operation data. | Steam Contamination | Version 2.5 | no | yes |  | w | NR | Motor Stator
CENOVUS | G09P02 | 2022-06-20 | 168Hp | 1000m3 | 220°C | SJ8000 47 STAGE | 830m | 66 | failed elect | 2022-08-25 | Tear down Completed; Seal shaft was not broken, the system held pressure test, Stator was found short. Seal, motor and BMB had well fluid (bitumen and water). The Stator was not dissected to locate the fault, but the short is a result of well fluid contamination due to cycling, as shown in the production data. | Downhole Short | Version 3.0 | no |  |  | w | NR | Seal
CENOVUS | L02P06 | 2022-06-29 | 168Hp | 1000m3 | 220°C | SJ8000 47 STAGE | 570m | 144 | failed | 2022-11-20 | lower meg readings at landing | Downhole Short | Version 3.0 | no |  |  | w | NR | Seal
CENOVUS | B07P17 | 2022-07-11 | 84Hp | 450m3 | 210°C | SJ4200 42 STAGE | 650m | 106 | failed | 2022-10-25 | utilizing ver 2.5 for trial purpose to get run time | Downhole Short | Version 2.5 | no |  |  | w | NR | Seal
CENOVUS | B13P05 | 2022-07-23 | 60hp | 400m3 | 210°C | SJ2800 38 STAGE | 575m | 331 |  |  |  |  | Version 3.0 | no |  |  | w | R
CENOVUS | E26P10 | 2022-07-30 | 132Hp | 950m3 | 220°C | SJ8000 47 STAGE | 930m | 324 |  |  | aviation bomb found on location standby |  | Version 3.0 | no |  |  | w | R
CENOVUS | W29P01 | 2022-07-31 | 132Hp | 1000m3 | 240°C | SJ8000 47 STAGE | 958m | 37 | Failed Elect | 2022-09-06 |  | Downhole Short | Version 3.0 | no |  |  | w | NR | Seal
CENOVUS | J03P08 | 2022-08-08 | 84Hp | 600m3 | 210°C | SJ4200 36 STAGE | 605m | 315 |  |  |  |  | Version 3.0 | no |  |  | w | R
STRATHCONA | D02P07 | 2022-08-20 | 60Hp | 250m3 | 210°C | SJ2800 38 STAGE | 858m | 170 | failure | 2023-02-06 | using backup 3 | Downhole Short | Version 2.5 | no |  |  | w | NR | Motor Stator
CONOCO | 263-1 P04 | 2022-08-28 | 60hp | 775m3 | 210°C | SJ6500 23 STAGE | 540m | 295 |  |  |  |  | Version 3.0 | no |  |  | w | R
SUNCOR | 5P8 | 2022-09-17 | 60Hp | 600m3 | 198°C | SJ4200 18 STAGE | 480m | 275 |  |  |  |  | Version 2.5 | no |  |  | w | R
CENOVUS | B07P14 | 2022-10-07 | 108Hp | 500m3 | 225°C | SJ5500 41 STAGE | 580 | 255 |  |  |  |  | Version 3.0 | no |  |  | w | R |  | 173000
STRATHCONA | D02P08 | 2022-11-04 | 60Hp | 700m3 | 210°C | SJ2800 38 STAGE/SGNPSH | 915m | 101 | electrical failure | 2023-02-13 | backup #4 used for this system | Downhole Short | Version 2.5 | new screen |  |  | w | NR | Seal | 216366
CENOVUS | W19P10-1 | 2022-11-06 | 168Hp | 800m3 | 235°C | SJ8000 53 STAGE | 820 | 225 | electrical failure | 2023-05-15 |  | Unknown | Version 3.0- New screen | new screen |  |  | w | NR | Unknown | 188240
CONOCO | 262-2P02 | 2022-11-19 | 84HP | 840m3 | 205°C | SJ6500 33 STAGE | 650m | 212 |  |  |  |  | Version 3.0- New screen | new screen |  |  | w | R |  | 236068.46
CONOCO | 261-3 P11 | 2022-12-03 | 60HP | 740m3 | 205°C | SJ5500 29 STAGE | 620m | 198 |  |  | backup #4 for strathcona for shelf |  | Version 3.0- New screen | new screen |  |  | w | R |  | 191000
CNRL | E3P | 2022-12-29 | 108HP | 700m3 | 227°C | SJ5500 47 STAGE | 776m | 41 | electrical failure | 2023-02-08 | motor winding/seal flood | Unknown | Version 3.0- New screen | new screen |  |  | w | NR | Unknown | 189314.63
STRATHCONA | 206p06 | 2023-01-11 | 60HP | 350m3 | 215 | SJ2800 22 stage/sgnpsh | 660m | 159 | electrical failure | 2023-05-22 | lots of steam and flashing on this well | Unknown | Version 2.5 | new screen |  |  | w | NR | Unknown | 192120.68
STRATHCONA | D03P06 | 2023-01-28 | 60HP | 250m3 | 210°C | SJ2800 45 STAGE/SGNPSH | 809m | 57 | failed | 2023-03-26 |  | Unknown | Version 2.5 | new screen |  |  | w | NR | Unknown | 57000
STRATHCONA | 204P10 | 2023-02-17 | 84HP | 430m3 | 215°C | SJ4200 24 stage | 890m | 85 | failed | 2023-05-13 | run in hole, shorted 2 times, 3rd charm damaged hanger | Unknown | Version 3.0- New screen |  |  |  | w | NR | Unknown | 358478.3
HARVEST | 102-P02 | 2023-04-03 | 60HP | 350m3 | 235°C | SJ2800 38 stage D-15 | 570m | 77 |  |  |  |  | ver 3.5- New screen |  |  |  | w | R |  | 185157.68
Suncor | 3P2 | 2023-05-18 | 60HP | 450m3 | 200°C | SJ2800 22 Stage | 410m | 32 |  |  |  |  | ver 3.5- New screen |  |  |  | w | R |  | 155000

## Survivability Data (hidden)
RUNTIME (Excel Calculated) | SEAL | W/L | Failure Count | 1-n/d | Failure Count | #REF! | Probability of Survival for Time | S(t) Steps
615m | Well Fluid Contamination | w |  |  | 0
810m |  | w
519m | Downhole Short | w
589m | Well Fluid Contamination | w
629m | Well Fluid Contamination | w
616m | Overheating | w
455m | Idle Amps | w
655m | No Production | w
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
600m | Downhole Short | w
1016m | No Production | w
629m | Well Fluid Contamination | w
600m | Downhole Short | w
810m | No Production | w
500m |  | w
549m | Unknown | w
370m | Rebuild | w
#REF! | #REF! | #REF! | #REF! | #REF!
375m | No Production | w
745m |  | w
950m | Downhole Short | w
915m | Downhole Short | w
858m | Steam Contamination | w
830m | Downhole Short | w
570m | Downhole Short | w
650m | Downhole Short | w
575m |  | w
930m |  | w
958m | Downhole Short | w
605m |  | w
858m | Downhole Short | w
540m |  | w
480m |  | w
580 |  | w
915m | Downhole Short | w
820 | Unknown | w
650m |  | w
620m |  | w
776m | Unknown | w
660m | Unknown | w
809m | Unknown | w
#REF! | #REF! | #REF! | #REF! | #REF!
890m | Unknown | w
570m |  | w
410m |  | w
#REF! | #REF! | #REF! | #REF! | #REF!
6 | Version 3.5 | w
746m

## Failure Data (hidden)
SEAL | #REF! | W/L | R/NR/Waiting | Reason for Pull | SEAL | New Screen | R/NR/Waiting | Failure Points | Reason for Pull
Well Fluid Contamination | Version 1 | w | NR | The cause for the downhole short is likely attributed to a well fluid contamination burn in the motor stator. The well fluid contamination throughout the system resulted from a seal failure likely due to low/no flow events throughout the operation | #REF!
| Version 1 | w | R | 0
Downhole Short | Version 1 | w | NR | The cause for the downhole short is likely attributed to the presence of conductive/low dielectric fluid and insulation degradation resulting in the burn in the motor stator and ultimately failed the system. The well fluid appears to have traversed the seal section.
Well Fluid Contamination | Version 1 | w | NR | The cause for the electrical failure in the motor that the system was pulled for was due to well fluid contamination into the motor. The reason for well fluid contamination was due to exceeding volumetric capacity of the motor oil contained in the seal, motor and below motor bellows under vacuum during thermal contraction, which exceeded the differential pressure limitations of upper guide mechanical shaft seal and duel nested bellows
Well Fluid Contamination | Version 1 | w | NR | The cause for the downhole short can be attributed to a well fluid contamination burn in the Pothead. The well fluid contamination throughout the system resulted from a seal pressurization failure due to low/no flow events during an abnormal amount of no production events throughout the operation.
Overheating | Version 1 | w | NR | The cause for the electrical failure found in the motor was a direct result of overheating, and the overheating is most likely due to the ESP operating for an extended period under extreme load fluctuation conditions (for the last four days of operation). It is unknown if this type of operation was intended (manual) or if there was a surface equipment issue with the drive/controller.
Idle Amps | Version 1 | w | NR | 0
No Production | Version 1 | w | NR | The cause of the No production/Idle Amps was a broken shaft in the seal; The broken shaft was due to excessive mechanical heat transfer from a seized radial support bearing in the seal head due to loss of lubricity impacted by sand accumulation in the upper lab section.
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
Downhole Short | Version 1 | w | NR | The cause of the downhole short is attributed to the presence of conductive fluid (water and bitumen) and insulation degradation in the motor; the short was located just below the motor female pins.
No Production | Version 2 | w | NR | The cause for the down hole short for which this unit was pulled can be attributed to a contamination burn in the head end of the motor that was a result of a seal pressurization failure and probable insulation degradation to motor components from low/no flow events during an abnormal amount of no production ride through operation.
Well Fluid Contamination | Version 2 | w | NR | The cause for the downhole short is likely attributed to a well fluid contamination burn in the motor stator. The well fluid contamination throughout the system resulted from the seal failure likely due to low/no flow events throughout the operation combined with reduced seal volumetric flow equalization rates.
Downhole Short | Version 1 | w | NR | 0
No Production | Version 1 | w | NR | system is stabilized, start up issues change pcp
| Version 1 | w | R | 0
Unknown | Version 2 | w | NR | electrically failed
Rebuild | Version 2.5 | w | NR | pulled and rebuilding to run in another
#REF! | #REF! | #REF! | #REF! | #REF!
No Production | Version 2.5 | w | NR | failed broken shaft, no prod both ways
| Version 2.5 | w | R | 0
Downhole Short | Version 2.5 | w | NR | bucket system going back in baker
Downhole Short | Version 2.5 | w | NR | using backup 2
Steam Contamination | Version 2.5 | w | NR | Tear down Completed; Seal shaft was not broken, the system held pressure test, Stator was found shorted, found burn at the upper-end coil of Stator also, found water in the seal, motor and BMB, no bitumen in the system, most probably steam entered the system as a result of stator short /explosion. When the unit was retrieved, steam was converted into water. Burn in Stator can be either due to handling during assembly or heat from the operation, waiting on operation data.
Downhole Short | Version 3.0 | w | NR | Tear down Completed; Seal shaft was not broken, the system held pressure test, Stator was found short. Seal, motor and BMB had well fluid (bitumen and water). The Stator was not dissected to locate the fault, but the short is a result of well fluid contamination due to cycling, as shown in the production data.
Downhole Short | Version 3.0 | w | NR | lower meg readings at landing
Downhole Short | Version 2.5 | w | NR | utilizing ver 2.5 for trial purpose to get run time
| Version 3.0 | w | R | 0
| Version 3.0 | w | R | aviation bomb found on location standby
Downhole Short | Version 3.0 | w | NR | 0
| Version 3.0 | w | R | 0
Downhole Short | Version 2.5 | w | NR | using backup 3
| Version 3.0 | w | R | 0
| Version 2.5 | w | R | 0
| Version 3.0 | w | R | 0
Downhole Short | Version 2.5 | w | NR | backup #4 used for this system
Unknown | Version 3.0- New screen | w | NR | 0
| Version 3.0- New screen | w | R | 0
| Version 3.0- New screen | w | R | backup #4 for strathcona for shelf
Unknown | Version 3.0- New screen | w | NR | motor winding/seal flood
Unknown | Version 2.5 | w | NR | lots of steam and flashing on this well
Unknown | Version 2.5 | w | NR | 0
#REF! | #REF! | #REF! | #REF! | #REF!
Unknown | Version 3.0- New screen | w | NR | run in hole, shorted 2 times, 3rd charm damaged hanger
| Version 3.5 | w | R | 0
| Version 3.5 | w | R | 0
#REF! | #REF! | #REF! | #REF! | #REF!
Version 3.5 | #REF! | w | R | 0
| #REF! |  | w | SLUGGER-latest seal section,used motor/cable
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
| #REF! |  |  | 0
0
0
0
0
0
0
0

## Normal Distribution- Data (hidden)
RUNTIME (Excel Calculated) | Version | W/L | Runtime | #REF!
615m | Well Fluid Contamination | w | N/A
810m | 0 | w
519m | Downhole Short | w
589m | Well Fluid Contamination | w
629m | Well Fluid Contamination | w
616m | Overheating | w
455m | Idle Amps | w
655m | No Production | w
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
600m | Downhole Short | w
1016m | No Production | w
629m | Well Fluid Contamination | w
600m | Downhole Short | w
810m | No Production | w
500m | 0 | w
549m | Unknown | w
370m | Rebuild | w
#REF! | #REF! | #REF! | #REF!
375m | No Production | w
745m | 0 | w
950m | Downhole Short | w
915m | Downhole Short | w
858m | Steam Contamination | w
830m | Downhole Short | w
570m | Downhole Short | w
650m | Downhole Short | w
575m | 0 | w
930m | 0 | w
958m | Downhole Short | w
605m | 0 | w
858m | Downhole Short | w
540m | 0 | w
480m | 0 | w
580 | 0 | w
915m | Downhole Short | w
820 | Unknown | w
650m | 0 | w
620m | 0 | w
776m | Unknown | w
660m | Unknown | w
809m | Unknown | w
#REF! | #REF! | #REF! | #REF!
890m | Unknown | w
570m | 0 | w
410m | 0 | w
#REF! | #REF! | #REF! | #REF!
6 | Version 3.5 | w
746m | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0
0
0
0
0
0
0
0
0
0